## Legend, definitions & instr
Main Objective
Calculate the demand for Service Center and HMH's capacity, ensuring the predictability needed to meet projects and to enable decisions to be made in advance.
Type | Definition
Firm | Projects with PO, or in other words, backlog
Risk Release | Forecasted projects, but evaluated in LOB to be as firm that it is initiated even with a PO
Forecast | Forecasted projects, in budget, however still not certain.
Avg hours per Phase | Average time consumption in hours expected per phase (considering transactional projects)
Avr Lead time per Phase | Average time consumption in mothns expected per phase (considering transactional projects)
Legends | FCTS | Forecast
| FIRM | Backlog (with PO)
The Ideal Design
RCCP Service Center - Premises / Rules
Demand Control | In this table, need to fill all projects and your informations.
In this table, have all months of the year, need to be distributed the total hours per total lead time, the formula is: (Avg Hours per Phase (Hours) * Quantity) / Avg Lead time Phase (Months).
We need to pay attention to filling the demand from the "start month".
In the demand table of the tab "RCCP SAM" is automatic, not need to fill.
Capacity Control | Need to calculate the capacity in relation of the workdays.
Overtime only occurs when demand is greater than capacity.
HMH capacity is calculated on one line, contractors on another and we have unavailable, which is a vacation reference value.
RCCP - Graphic | When filling in the data, you need to insert a text box with white letters in the RCCP graphic and enter the product line of the area.
The Graphic is automatized, we need only to fill the demand and capacity.
The Graphic have your values in thousand hours.
Projects Control
The table below it's necessary to fill all projects and your informations.
Distribution of Demand in hours
Calculations sources: | Definitions
Firm, Risk Release or Forecast | The distribution of hours is as below:
(Avg Hours per Phase (Hours) * Quantity) / Avg Lead time Phase (Months)
Ex: H-4 Connector
| Avg Hours per Phase (Hours) | 968
| Quantity | 2
| Avg Lead time Phase (Months) | 4
| Start Month | January
2025
| Jan | Fev | March | Apr
| 484 | 484 | 484 | 484
Note: Important to understand that this result need to be spread according to the lead time
Capacity Calculation in Hours
Calculations resources: | Definitions
HMH employee and contractors | For calculation HMH employees we use the formula below:
Operational Hours = ((Resource quantity)*(total workdays on the quarter) *(85% of total hours per day) - (Unavailable Hours))
For calculation Contractors employees we use the formula below:
Operational Hours = ((Resource quantity)*(total workdays on the quarter) *(85% of total hours per day) + (HMH Capacity))
For calculation Unavailable Hours, we use the formula below:
Total Unavailable Hours = {((Resource quantity)/4 [quantity quarter in one year])*(85% of total hours per day)*(average workdays per quarter in one year) + (offshore recovery Hours)}
Standard List - Project Overview Tab
Type | Product Line | Project Scope | Project Phase | Project Status | Month | Year | Report Location | Equipment
Firm | Pressure Control | FPA | D&I | Waiting PO | January-24 | 2024 | Kintore | H4 Connector
Forecast | Topside | Transactional | Repair | Waiting Parts | February-24 | 2025 | Kristiansand | Bonnet
Risk Release | Riser | Short Cycle | T&A | WIP | March-24 | 2026 | Baku | BOP Annular
N/A | Offshore | Offshore | FPA | Concluded | April-24 | 2027 | Erkelenz | Annular Piston
| Others |  | CSA | N/A | May-24 | 2028 | Lyngdal | Male Stab
|  |  | TCO | Waiting Requested | June-24 |  | Houston | Female Stab
|  |  | Manufacturing |  | July-24 |  | Mobile | Test Stump
|  |  | N/A |  | August-24 |  | UAE | Diverter
[5 empty] | September-24 |  | Macae | Ram Block
[5 empty] | October-24 |  | Singapore | Ram BOP
[5 empty] | November-24 |  | Brisbane | Telescopic Joint - QTR-3500
[5 empty] | December-24 |  |  | Telescopic Joint - MR6H
[5 empty] | January-25 |  |  | Riser Joint - QTR-3500
[5 empty] | February-25 |  |  | Riser Joint - LK - 3.5
[5 empty] | March-25 |  |  | Riser Joint - FT - H
[5 empty] | April-25 |  |  | DDM
[5 empty] | May-25 |  |  | Dolly
[5 empty] | June-25 |  |  | BRC Gripper Head
[5 empty] | July-25 |  |  | LGA Guide Head
[5 empty] | August-25 |  |  | Travelling Block
[5 empty] | September-25 |  |  | Rocker Arm
[5 empty] | October-25 |  |  | Crown Block (Sheave Cluster)
[5 empty] | November-25 |  |  | Drawworks Callipers (MB)
[5 empty] | December-25 |  |  | Drawworks Callipers (BKB)
[5 empty] | January-26 |  |  | Offshore
[5 empty] | February-26 |  |  | Drive Train
[5 empty] | March-26 |  |  | BRC Hydraulic Cylinders
[5 empty] | April-26 |  |  | PDPH Hydraulic Cylinders
[5 empty] | May-26 |  |  | AHC Cylinders
[5 empty] | June-26 |  |  | Kelly Valves
[5 empty] | July-26 |  |  | Shafts and Pumps
[5 empty] | August-26 |  |  | Wiresheaves
[5 empty] | September-26 |  |  | Riser Running Tool
[5 empty] | October-26 |  |  | Gas Handler
[5 empty] | November-26 |  |  | Goosenecks
[5 empty] | December-26 |  |  | Swivel
[5 empty] | January-27 |  |  | Bay Handling
[5 empty] | February-27 |  |  | Tensioner
[5 empty] | March-27 |  |  | Termination Adapter
[5 empty] | April-27 |  |  | Gearbox Drawworks
[5 empty] | May-27 |  |  | Roughnecks
[5 empty] | June-27 |  |  | Top Drives
[5 empty] | July-27 |  |  | Mud Pumps
[5 empty] | August-27 |  |  | Vertical Pipe Handlers
[5 empty] | September-27 |  |  | Horizontal Pipe Handlers
[5 empty] | October-27 |  |  | Torque Wrenches
[5 empty] | November-27 |  |  | Acess Baskets
[5 empty] | December-27 |  |  | DAT
Casings
Mandrel

## Projects Overview
Product Line | Equipment | Project Name | Quantity | Project Phase | Project Scope | Type | Project Status | Start Month | Start Year | Avg hours per Phase (Hours) | Avg Lead time phase (Months) | January-25 | February-25 | March-25 | April-25 | May-25 | June-25 | July-25 | August-25 | September-25 | October-25 | November-25 | December-25 | January-26 | February-26 | March-26 | April-26 | May-26 | June-26 | July-26 | August-26 | September-26 | October-26 | November-26 | December-26 | January-27 | February-27 | March-27 | April-27 | May-27 | June-27 | July-27 | August-27 | September-27 | October-27 | November-27 | December-27
Pressure Control | H4 Connector | TOI - H4 Connector - Transocean (From by sales) - SHD | 1 | FPA | FPA | Firm | Concluded | March-25 | 2025 | 1210 | 10 |  |  | 172.8571 | 172.8571 | 172.8571 | 172.8571 | 102 | 50 | 100 |  |  | 137 | 130 | 130
Pressure Control | H4 Connector | TOI - H4 Connector - Transocean (From by sales) - DWHD - Petrobras 1000 | 1 | FPA | FPA | Forecast | Waiting PO | March-26 | 2026 | 1168 | 3 | [14 empty] | 389.3333 | 389.3333 | 389.3333
Pressure Control | H4 Connector | TOI - H4 Connector - Transocean (From by sales) - ExF - Petrobras 1000 | 1 | FPA | FPA | Firm | WIP | November-25 | 2025 | 650 | 3 | [10 empty] | 350 | 150 | 150 | 90 | 40
Pressure Control | H4 Connector | TOI - H4 Connector - Transocean (From by sales) CX modificantion - DxE - SO 470005658 | 1 | FPA | FPA | Firm | Concluded | August-25 | 2025 | 533 | 4 | [7 empty] | 133.3333 | 133.3333 | 133.3333 | 133.3333
Pressure Control | H4 Connector | CON-H4 Connector ExF Amaralina Star - Constellation (From by Project) - 470005343 | 1 | FPA | FPA | Firm | Concluded | May-25 | 2025 | 1330 | 6 |  |  |  |  | 242 | 350 | 50 | 150 | 160 | 300 | 78
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by projects) | 1 | FPA | FPA | Firm | Concluded | February-25 | 2025 | 816 | 3 |  | 272 | 272 | 272
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by projects) | 1 | FPA | FPA | Firm | Concluded | February-25 | 2025 | 816 | 3 |  | 272 | 272 | 272
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by projects) | 1 | D&I | Transactional | Firm | Concluded | February-25 | 2025 | 100 | 1 |  | 100
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by projects) | 1 | D&I | Transactional | Firm | Concluded | February-25 | 2025 | 100 | 1 |  | 100
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by projects) - 470005332 | 1 | Repair | Transactional | Firm | WIP | June-25 | 2025 | 820 | 5 | [5 empty] | 172 | 100 | 100 | 144 | 184 | 150 | 150 | 70 | 30 | 70
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by projects) - 470005333 | 1 | Repair | Transactional | Firm | WIP | June-25 | 2025 | 700 | 5 | [5 empty] | 172 | 100 | 100 | 144 | 184 | 150 | 150 | 50
Pressure Control | Bonnet | CON-Bonnet 4604405 - Constellation (From by projects) | 1 | T&A | Transactional | Forecast | Waiting PO | April-26 | 2026 | 132 | 1 | [15 empty] | 132
Pressure Control | Bonnet | CON-Bonnet 4604427 - Constellation (From by projects) | 1 | T&A | Transactional | Forecast | Waiting PO | April-26 | 2026 | 132 | 1 | [15 empty] | 132
Pressure Control | H4 Connector | CON - Conector H4 - 4604268 - Constellation | 1 | T&A | Transactional | Forecast | Waiting Parts | March-26 | 2026 | 176 | 1 | [14 empty] | 176
Pressure Control | H4 Connector | CON - Conector H4 - 470000706 - Constellation | 1 | T&A | Transactional | Firm | Concluded | February-26 | 2025 | 176 | 2 | [11 empty] | 88 | 88
Pressure Control | Bonnet | CON-Bonnet 4604404 - Constellation (From by projects) | 1 | T&A | Transactional | Forecast | Waiting PO | April-26 | 2026 | 132 | 1 | [15 empty] | 132
Pressure Control | Bonnet | CON-Bonnet 4604380 - Constellation (From by projects) | 1 | T&A | Transactional | Forecast | Waiting PO | April-26 | 2026 | 132 | 1 | [15 empty] | 132
Pressure Control | Bonnet | CON-Bonnet 470001804 - Constellation (From by projects) | 1 | T&A | Transactional | Forecast | Waiting PO | May-26 | 2026 | 132 | 1 | [16 empty] | 132
Pressure Control | Bonnet | FOR-Bonnet 15-3K 470002470- Foresea (From by projects) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 1068 | 8 |  |  | 117 | 117 | 117 | 100 | 100 | 100 | 117 | 150 | 150
Pressure Control | Bonnet | FOR-Bonnet 15-3K 470002553- Foresea (From by projects) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 1068 | 8 |  |  | 117 | 117 | 117 | 100 | 100 | 100 | 117 | 150 | 150
Pressure Control | Annular Piston | VLS - Annular Piston - Valaris (From by projects) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 396 | 4 | 99 | 99 | 99 | 99
Pressure Control | Female Stab | CON-Female Stab - Manufacturing Process | 1 | Manufacturing | Transactional | Firm | WIP | February-26 | 2026 | 125 | 1 | [14 empty] | 125
Pressure Control | Female Stab | CON-Female Stab - Complete (From by Projects) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 564.5 | 1 | [5 empty] | 564.5
Pressure Control | Female Stab | CON-Female Stab - Piston (From by Projects) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 124.5 | 1 |  |  |  | 124.5
Pressure Control | Ram Block | CON - Ram Block - Constellation - 470004598 (From by sales) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 100 | 1 |  | 100
Pressure Control | Ram Block | CON - Ram Block - Constellation - 470004599 (From by sales) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 100 | 1 |  | 100
Pressure Control | Ram Block | CON - Ram Block - Constellation - 470004600 (From by sales) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 100 | 1 |  | 100
Pressure Control | Ram Block | CON - Ram Block - Constellation - 470004099 (From by Project) | 1 | FPA | FPA | Firm | Concluded | February-26 | 2025 | 386 | 2 |  |  | 193 | 193
Pressure Control | Ram Block | CON - Ram Block - Constellation - 470004598 (From by Project) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 400 | 4 | [5 empty] | 100 | 200 | 67 | 33
Pressure Control | Ram Block | CON - Ram Block - Constellation - 470004599 (From by Project) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 440 | 6 |  |  |  |  | 88 | 72 | 150 | 50 | 40 | 40
Pressure Control | Ram Block | CON - Ram Block - Constellation - 470004600 (From by Project) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 440 | 5 | [5 empty] | 100 | 200 | 67 | 33 | 40
Pressure Control | Ram Block | CON - Ram Block - Constellation - 470004100 (From by Project) | 1 | FPA | FPA | Firm | Concluded | February-26 | 2025 | 386 | 3 |  |  | 128.6667 | 128.6667 | 128.6667
Riser | Riser Joint - FT - H | 35J Inspeção Laguna Star, do lote de 41J | 35 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 64 | 4 |  |  |  |  | 142 | 1443 | 448 | 200
Riser | Riser Joint - FT - H | 6J Inspeção Laguna Star, pendentes do lote de 41J | 6 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 45 | 1 | [9 empty] | 270
Riser | Riser Joint - FT - H | 25J Montagem laguna Star com Amaralina | 25 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 150 | 1 | [8 empty] | 3750
Riser | Riser Joint - FT - H | 7J teste/montagem Laguna Star - Minor Repair | 7 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 150 | 1 | [9 empty] | 1050
Riser | Riser Joint - FT - H | 17J Inspeção Amaralina Star, do lote de 34J | 17 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 64 | 3 |  |  |  |  | 113 | 720 | 264
Riser | Riser Joint - FT - H | 24J Inspeção Amaralina Star | 24 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 45 | 1 | [9 empty] | 1080
Riser | Riser Joint - FT - H | 39J SPS Inspeção Amaralina Star, juntas que virão para onshore | 39 | CSA | Short Cycle | Firm | WIP | January-26 | 2026 | 150 | 1 | [12 empty] | 5850
Others | Casings | 110 Casings 12m com 22" - Baker Hughes | 84 | D&I | Short Cycle | Firm | Concluded | February-26 | 2025 | 7.36 | 2 | [11 empty] | 309.12 | 309.12
Riser | Riser Joint - FT - H | 30J SPS Amaralina Star - Minor Repair | 30 | CSA | Short Cycle | Firm | WIP | January-26 | 2026 | 88 | 2 | [12 empty] | 100 | 410
Riser | Riser Joint - FT - H | 20J SPS Amaralina Star - Major Repair | 20 | CSA | Short Cycle | Firm | WIP | February-26 | 2026 | 310 | 2 | [13 empty] | 3100 | 3100
Riser | Riser Joint - FT - H | 4J Amaralina Star onshore - Minor repair | 4 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 30 | 1 | [11 empty] | 120
Riser | Riser Joint - FT - H | 8J Amaralina Star onshore - Major Repair | 8 | CSA | Short Cycle | Firm | Concluded | November-25 | 2025 | 370 | 2 | [10 empty] | 1480 | 1480
Riser | Riser Joint - FT - H | 57J SPS Laguna Star - Minor Repair | 57 | CSA | Short Cycle | Firm | WIP | November-26 | 2026 | 88 | 2 | [22 empty] | 2508 | 2508
Riser | Riser Joint - FT - H | 5J Amaralina Star onshore - Major Repair | 5 | CSA | Short Cycle | Firm | WIP | January-26 | 2026 | 310 | 1 | [12 empty] | 1550
Riser | Riser Joint - FT - H | 4J Amaralina Star Onshore - Major Repair | 4 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 370 | 2 | [9 empty] | 740 | 740
Riser | Riser Joint - FT - H | 4J Amaralina Star onshore - Minor Repair | 4 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 30 | 2 | [9 empty] | 60 | 60
Riser | Riser Joint - FT - H | 30J Amaralina Star Onshore - Major Repair | 30 | CSA | Short Cycle | Firm | Concluded | December-25 | 2025 | 370 | 1 | [11 empty] | 11100
Riser | Riser Joint - FT - H | 11J Amaralina Star Onshore Base Line Inspection | 11 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 45 | 1 | [10 empty] | 495
Riser | Riser Joint - FT - H | 30J Inspeção Brava Star | 30 | CSA | Short Cycle | Firm | WIP | December-25 | 2025 | 45 | 1 | [11 empty] | 1350
Riser | Riser Joint - FT - H | 25J Minor Repair and Assembly Brava Star | 25 | CSA | Short Cycle | Firm | WIP | January-26 | 2026 | 88 | 2 | [12 empty] | 1100 | 1100
Riser | Riser Joint - FT - H | 22J Minor Repair and Assembly Brava Star | 22 | CSA | Short Cycle | Firm | WIP | April-26 | 2026 | 88 | 2 | [15 empty] | 968 | 968
Riser | Riser Joint - FT - H | 10J Major Repair and Assembly Brava Star | 10 | CSA | Short Cycle | Firm | WIP | February-26 | 2026 | 310 | 2 | [13 empty] | 1000 | 2100
Riser | Riser Joint - FT - H | 45J Inspeção Brava Star | 45 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 35 | 3 |  |  |  |  | 88 | 704 | 785
Riser | Riser Joint - FT - H | 23J teste/montagem Brava Star | 23 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 77 | 1 | [6 empty] | 1781
Riser | Riser Joint - FT - H | 10J teste/montagem Brava Star | 10 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 40 | 1 | [7 empty] | 400
Riser | Riser Joint - FT - H | 5J Major Repair Laguna Star - From by offshore - Lote 2 of January | 5 | CSA | Short Cycle | Firm | WIP | January-26 | 2026 | 310 | 2 | [12 empty] | 775 | 775
Riser | Riser Joint - FT - H | 3J Reparo Laguna Star - From by offshore - Lote 1 of December | 3 | CSA | Short Cycle | Firm | WIP | February-26 | 2025 | 370 | 1 | [11 empty] | 1110
Riser | Riser Joint - FT - H | 7J Reparo Laguna Star | 7 | CSA | Short Cycle | Firm | Concluded | October-25 | 2025 | 370 | 2 | [9 empty] | 1295 | 1295
Topside | Telescopic Joint - QTR-3500 | CON - TJ GDS-B - Constellation (From by sales) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 960 | 2 |  |  |  |  | 480 | 480
Topside | Telescopic Joint - QTR-3500 | CON - TJ APS-001 - Constellation (From by sales) | 1 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 450 | 1 |  | 450
Riser | Riser Joint - QTR-3500 | 10J Repair Scope - CSA - Constellation | 10 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 460 | 3 | [6 empty] | 1850 | 1850 | 900 | 450
Riser | Riser Joint - QTR-3500 | 128 Preservation Scope - CSA - Constellation (From by project) | 128 | CSA | Short Cycle | Firm | Concluded | October-25 | 2025 | 25 | 2 | [9 empty] | 1600 | 1600
Riser | Riser Joint - QTR-3500 | 30J CSA Gold Star - RiCon (From by project) | 30 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 30 | 1 |  |  |  | 900
Riser | Riser Joint - QTR-3500 | 123J CSA Lone Star - RiCon (From by project) | 123 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 100 | 2 | 6150 | 6150
Riser | Riser Joint - QTR-3500 | 44J CSA Alpha Star - RiCon (From by project) | 44 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 100 | 2 |  | 2200 | 2200
Riser | Riser Joint - QTR-3500 | 88 módulos de flutuadores (From by project) | 88 | Repair | Short Cycle | Firm | Concluded | February-26 | 2025 | 20 | 2 | [5 empty] | 880 | 880
Riser | Riser Joint - QTR-3500 | 36J Rework Alpha Star (From by project) | 36 | T&A | Transactional | Firm | Concluded | February-26 | 2025 | 30 | 1 |  | 1080
Riser | Riser Joint - QTR-3500 | 36J CSA Alpha Star - RiCon (From by project) | 36 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 30 | 1 |  |  |  | 1080
Riser | Riser Joint - LK - 3.5 | 2J Repair Scope from 14J D&I 2Y- Noble (From by projects team) | 2 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 300 | 1 |  | 600
Riser | Riser Joint - LK - 3.5 | 36J Preservation - Noble (From by projects team) | 36 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 20 | 2 | [8 empty] | 360 | 180 | 180
Topside | BRC Gripper Head | NBL - Gripper Head - Noble - GPH-1 (From by sales) | 1 | D&I | Transactional | Firm | WIP | February-26 | 2026 | 160 | 1 | [13 empty] | 160
Topside | BRC Gripper Head | NBL - Gripper Head - Noble - GPH-1 (From by sales) | 1 | Repair | Transactional | Forecast | Waiting PO | April-26 | 2026 | 600 | 2 | [15 empty] | 300 | 300
Topside | BRC Gripper Head | NBL - Gripper Head - Noble - GPH-1 (From by sales) | 1 | T&A | Transactional | Forecast | Waiting PO | July-26 | 2026 | 208 | 1 | [18 empty] | 208
Topside | BRC Gripper Head | NBL - Gripper Head - Noble - GPH-2 (From by sales) | 1 | D&I | Transactional | Firm | Waiting Parts | March-26 | 2026 | 160 | 1 | [14 empty] | 160
Topside | BRC Gripper Head | NBL - Gripper Head - Noble - GPH-2 (From by sales) | 1 | Repair | Transactional | Forecast | Waiting PO | May-26 | 2026 | 600 | 2 | [16 empty] | 300 | 300
Topside | BRC Gripper Head | NBL - Gripper Head - Noble - GPH-2 (From by sales) | 1 | T&A | Transactional | Forecast | Waiting PO | July-26 | 2026 | 208 | 1 | [18 empty] | 208
Others | Torque Wrenches | FOR - Assembly and Adjust RNX - Norbe IX | 1 | T&A | Transactional | Forecast | Waiting PO | February-26 | 2026 | 350 | 2 | [14 empty] | 175 | 175
Topside | BRC Gripper Head | PRIO - Gripper Head - PRIO (From by sales) | 1 | Repair | Transactional | Firm | WIP | December-25 | 2025 | 968 | 3 | [11 empty] | 322.6667 | 200 | 200 | 100 | 146
Topside | BRC Gripper Head | Equinor - Gripper Head - Equinor - Peregrino C | 1 | FPA | FPA | Forecast | Waiting PO | March-26 | 2026 | 968 | 3 | [14 empty] | 322.6667 | 322.6667 | 322.6667
Topside | LGA Guide Head | PRIO - LGA Guide Head - Prio (From by project team) | 1 | Repair | Transactional | Firm | WIP | December-25 | 2025 | 997 | 4 | [10 empty] | 249.25 | 249.25 | 180 | 180 | 138 | 140
Topside | Travelling Block | FOR - Travelling Block - Foresea (From by sales) | 1 | FPA | FPA | Firm | Concluded | February-26 | 2025 | 1090 | 9 | 105.7143 | 105.7143 | 105.7143 | 105.7143 | 105.7143 | 105.7143 | 105.7143 | 150 | 200
Topside | Travelling Block | FOR - Travelling Block - Foresea ODN I (From by sales) | 1 | FPA | FPA | Forecast | Waiting PO | May-26 | 2026 | 704 | 3 | [16 empty] | 234.6667 | 234.6667 | 234.6667
Topside | Crown Block (Sheave Cluster) | FOR - Sheave Cluster - Norbe VIII (From by sales) | 1 | FPA | FPA | Firm | Concluded | February-26 | 2025 | 1808 | 8 |  | 234.6667 | 234.6667 | 234.6667 | 234.6667 | 234.6667 | 234.6667 | 100 | 300
Topside | Crown Block (Sheave Cluster) | FOR - Sheave Cluster - ODN I (From by sales) | 1 | FPA | FPA | Forecast | Waiting PO | May-26 | 2026 | 704 | 3 | [16 empty] | 234.6667 | 234.6667 | 234.6667
Topside | Drawworks Callipers (MB) | 2x Brake Callipers - Foresea (From by Projects) | 2 | FPA | FPA | Firm | Concluded | February-26 | 2025 | 66 | 1 |  |  | 132
Topside | DAT | VEN - DAT - Ventura Victoria (From by sales) | 1 | D&I | Transactional | Forecast | Waiting PO | March-26 | 2026 | 98 | 1 | [14 empty] | 98
Topside | Drawworks Callipers (MB) | 8x Brake Callipers - Noble - Ocean Courage (From by projects) | 8 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 20 | 1 | [5 empty] | 160
Topside | Drawworks Callipers (MB) | 8x Brake Callipers - Noble - Ocean Courage (From by projects) | 8 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 20 | 1 | [6 empty] | 160
Topside | Drawworks Callipers (MB) | 4x Brake Callipers - Ventura (From by sales) | 4 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 20 | 1 | [5 empty] | 80
Topside | Drawworks Callipers (MB) | 4x Brake Callipers - Ventura (From by sales) | 4 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 20 | 1 | [8 empty] | 80
Others | Offshore | 4 Employee - January | 4 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 | 440
Others | Offshore | 4 Employee - February | 4 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 |  | 440
Others | Offshore | 4 Employee - March | 4 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 |  |  | 440
Others | Offshore | 8 Employee - April | 8 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 |  |  |  | 880
Others | Offshore | 8 Employee - May | 8 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 |  |  |  |  | 880
Others | Offshore | 4 Employee - June | 4 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 | [5 empty] | 440
Others | Offshore | 3 Employee - July | 3 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 | [6 empty] | 330
Others | Offshore | 7 Employee - August | 7 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 | [7 empty] | 770
Others | Offshore | 4 Employee - September | 4 | N/A | Offshore | Firm | Concluded | February-26 | 2025 | 110 | 1 | [8 empty] | 440
Others | Offshore | 6 Employee - October | 6 | N/A | Offshore | Firm | WIP | February-26 | 2025 | 110 | 1 | [9 empty] | 660
Others | Offshore | 3 Employee - November | 3 | N/A | Offshore | Firm | WIP | February-26 | 2025 | 110 | 1 | [10 empty] | 330
Others | Offshore | 2 Employee - December | 2 | N/A | Offshore | Firm | WIP | February-26 | 2025 | 110 | 1 | [11 empty] | 220
Topside | Drawworks Callipers (MB) | NBL - 8x Brake Callipers - Noble (From by Sales) | 8 | D&I | Transactional | Forecast | Waiting PO | June-26 | 2026 | 20 | 1 | [17 empty] | 160
Topside | Drawworks Callipers (MB) | 4x Brake Callipers - Ventura (From by Projects) - 470005493 | 4 | T&A | Transactional | Forecast | Waiting Parts | March-26 | 2026 | 20 | 1 | [14 empty] | 80
Others | Torque Wrenches | SLB - Torque Wrench - SLB (From by projects team) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 440 | 2 |  |  | 220 | 220
Others | Goosenecks | VLS - 3x Goosenecks - Valaris (From by projects team) | 3 | Repair | Transactional | Forecast | Waiting PO | March-26 | 2026 | 150 | 2 | [14 empty] | 225 | 225
Topside | BRC Gripper Head | FOR-Gripper Head N08 - Foresea | 1 | Repair | Transactional | Firm | WIP | February-26 | 2025 | 1680 | 10 |  | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 142.8571 | 43 | 100 | 400 | 280 | 100
Topside | BRC Gripper Head | FOR-Gripper Head ODN1 - Foresea | 1 | Repair | Transactional | Firm | WIP | March-25 | 2025 | 1680 | 10 |  |  | 166.6667 | 166.6667 | 166.6667 | 166.6667 | 166.6667 | 67 | 100 | 400 | 50 | 100 | 130 | 30 | 70
Topside | Telescopic Joint - MR6H | VLS - TJ DS-04B - Valaris - Fase 1 | 1 | Repair | Transactional | Firm | WIP | August-25 | 2025 | 2400 | 4 |  |  |  |  | 200 |  |  | 200 | 1000 | 200 | 100 | 100 | 100
Pressure Control | Ram Block | FOR - Ram Block - Foresea - 470005904 - (From by Project) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 100 | 1 | [7 empty] | 100
Topside | Telescopic Joint - MR6H | VLS - TJ DS-04B - Valaris - Fase 2 | 1 | T&A | Transactional | Firm | WIP | March-26 | 2026 | 650 | 2 | [14 empty] | 350 | 300
Pressure Control | Ram Block | VEN - Ram Block - Foresea - 470005904 - (From by Project) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 400 | 2 | [9 empty] | 200 | 200
Pressure Control | Ram Block | CON - Ram Block - 470001888 - Constellation | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 500 | 8 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5
Pressure Control | Ram Block | CON - Ram Block - 470001897 - Constellation | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 500 | 8 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5
Pressure Control | Ram Block | CON - Ram Block - 470001885 - Constellation | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 500 | 8 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5
Pressure Control | Ram Block | CON - Ram Block - 470001905 - Constellation | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 500 | 8 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5 | 62.5
Pressure Control | Diverter | CON - Diverter LNS - Constellation | 1 | FPA | FPA | Firm | WIP | February-26 | 2026 | 650 | 2 | [13 empty] | 500 | 150
Pressure Control | Diverter | CON - Diverter FS21 - APS - Constellation | 1 | Repair | Transactional | Firm | Concluded | January-25 | 2025 | 308 | 1 | 308
Pressure Control | BOP Annular | VEN - BOP Annular - Ventura (From by sales) - Carolina | 1 | D&I | Transactional | Forecast | Waiting PO | March-26 | 2026 | 176 | 1 | [14 empty] | 176
Pressure Control | BOP Annular | CON - BOP Annular - Constellation (From by projects) - Lone Star - COS Scope | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 120 | 1 | [10 empty] | 120
Pressure Control | BOP Annular | CON - BOP Annular - Constellation (From by projects) - Lone Star - COS Scope - Fase 2 | 1 | Repair | Transactional | Firm | Concluded | January-26 | 2025 | 190 | 1 | [11 empty] | 20 | 170
Pressure Control | BOP Annular | CON - BOP Annular - Constellation (From by projects) - Lone Star - COS Scope - Fase 3 | 1 | T&A | Transactional | Firm | Concluded | January-26 | 2026 | 132 | 1 | [12 empty] | 100 | 32
Pressure Control | BOP Annular | FOR - BOP Annular Foresea (From by sales) - Norbe VI - Fase 3 | 1 | T&A | Transactional | Forecast | Waiting PO | May-26 | 2026 | 132 | 1 | [16 empty] | 132
Pressure Control | BOP Annular | FOR - BOP Annular Foresea (From by sales) - Norbe VI - Fase 2 | 1 | Repair | Transactional | Firm | WIP | February-26 | 2026 | 854 | 4 | [13 empty] | 120 | 180 | 278 | 278
Pressure Control | BOP Annular | FOR - BOP Annular Foresea (From by sales) - Norbe VI | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 176 | 1 | [10 empty] | 176
Pressure Control | BOP Annular | FOR-BOP Annular N06 - Foresea | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 392.4 | 3 | 130.8 | 130.8 | 130.8
Pressure Control | BOP Annular | CON-BOP Annular 470001736 - Constellation | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 392.4 | 3 | 130.8 | 130.8 | 130.8
Pressure Control | Bonnet | FOR-Bonnet 15-3K 470002474 - Foresea | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 352 | 3 |  |  | 117.3333 | 117.3333 | 117.3333
Pressure Control | Annular Piston | CON-Annular Piston GX - 4603341 - Constellation | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 234.67 | 4 | 58.6675 | 58.6675 | 58.6675 | 58.6675
Riser | Riser Joint - LK - 3.5 | 31J Buoyancy Repair- Noble (From by projects team) | 31 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 66.67 | 1 | 2066.77
Riser | Riser Joint - LK - 3.5 | 6J repair from 31J D&I 2y - Noble | 6 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 70.67 | 1 | 424.02
Topside | Telescopic Joint - QTR-3500 | CON - TJ GDS-A - Constellation(From by Project) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 1800 | 3 | 600 | 600 | 600
Topside | Telescopic Joint - QTR-3500 | CON - TJ LNS-001 - Constellation(From by Project) | 1 | T&A | Transactional | Firm | Concluded | February-26 | 2025 | 1200 | 2 | 600 | 600
Topside | Telescopic Joint - QTR-3500 | CON - TJ GDS-A - Constellation(From by Project) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 1500 | 5 |  |  | 300 | 300 | 300 | 300 | 300
Topside | Telescopic Joint - QTR-3500 | CON - TJ GDS-A - Constellation(From by Project) | 1 | T&A | Transactional | Firm | Concluded | February-26 | 2025 | 500 | 1 | [6 empty] | 400 | 100
Topside | DDM | FOR - DDM 1000 N09 - Foresea | 1 | FPA | FPA | Firm | Concluded | November-24 | 2024 | 6045 | 9 | 671.6667 | 671.6667 | 671.6667 | 671.6667 |  | 671.6667 | 671.6667 | 671.6667 | 472 | 250 | 150 | 20 | 60
Pressure Control | H4 Connector | CON - Adequação Wear Ring GDS - Constellation - 470005600 (From by Projects) | 1 | Repair | Short Cycle | Forecast | Waiting Parts | March-26 | 2026 | 120 | 1 | [14 empty] | 120
Riser | Riser Joint - QTR-3500 | CON - Pup Check Valve Modification APS-128 - Constellation - 470005601 (From by Projects) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 400 | 2 | [7 empty] | 200 | 200
Topside | Termination Adapter | CON - Riser Adapter + Kick Out Pipes - Contellation - 470005402 (From by Projects) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 200 | 1 | [5 empty] | 200
Topside | Female Stab | CON-Female Stab - Complete (From by Projects) | 1 | Repair | Transactional | Firm | WIP | February-26 | 2025 | 1080 | 4 | [8 empty] | 360 | 360 | 200 | 160 | 150
Topside | Termination Adapter | CON - Riser Adapter + Kick Out Pipes - Contellation - 470005402 (From by Projects) | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 200 | 2 | [6 empty] | 100 | 100
Topside | Female Stab | CON-Female Stab - Complete (From by Projects) | 1 | T&A | Transactional | Firm | Concluded | February-26 | 2026 | 150 | 1 | [13 empty] | 150
Others | Termination Adapter | CON - Riser Adapter + Kick Out Pipes - Contellation - 470005402 (From by Projects) | 1 | T&A | Transactional | Firm | Concluded | February-26 | 2025 | 40 | 1 | [7 empty] | 40
Others | Gas Handler | Facilities demand - Coating HMH Yard | 1 | D&I | Short Cycle | Firm | Concluded | February-26 | 2025 | 774 | 2 | [6 empty] | 574 | 200
Topside | Telescopic Joint - QTR-3500 | CON - TJ LNS-002 - Constellation (From by Project) | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 1170 | 3 | [7 empty] | 560 | 560 | 50
Riser | Riser Joint - LK - 3.5 | NBL - Pup Joint 54495 - Noble | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 100 | 1 | [6 empty] | 100
Riser | Riser Joint - LK - 3.5 | 18J Preservation - Noble (From by projects team) | 18 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 10 | 1 | [9 empty] | 180 | 60
Riser | Riser Joint - LK - 3.5 | 15J 5 Years - Noble (From by projects team) | 15 | T&A | Transactional | Firm | Concluded | September-25 | 2025 | 20 | 2 | [8 empty] | 150 | 150
Riser | Riser Joint - LK - 3.5 | NBL - Pup Joint - 5ft - Noble | 1 | D&I | Transactional | Forecast | Waiting PO | March-26 | 2026 | 100 | 1 | [14 empty] | 100
Riser | Riser Joint - LK - 3.5 | NBL - Pup Joint - 10ft - Noble | 1 | D&I | Transactional | Forecast | Waiting PO | March-26 | 2026 | 100 | 1 | [14 empty] | 100
Riser | Riser Joint - LK - 3.5 | NBL - Pup Joint - 20ft - Noble | 1 | D&I | Transactional | Forecast | Waiting PO | March-26 | 2026 | 100 | 1 | [14 empty] | 100
Riser | Riser Joint - LK - 3.5 | NBL - Pup Joint 54495 - Noble | 1 | T&A | Transactional | Firm | WIP | February-26 | 2025 | 60 | 1 | [11 empty] | 60
Riser | Riser Joint - QTR-3500 | CON - Pup Joint Modification APS-118 - Constellation - 470005601 | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 400 | 2 | [7 empty] | 200 | 200
Pressure Control | H4 Connector | HMH - Inspection on Cylinders Head - Opportunity - 470005746 | 1 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 100 | 1 | [7 empty] | 100
Topside | Telescopic Joint - QTR-3500 | CON - TJ APS-001 - Constellation (From by Project) | 1 | D&I | Transactional | Firm | WIP | February-26 | 2026 | 960 | 3 | [12 empty] | 300 | 380 | 280
Topside | Telescopic Joint - QTR-3500 | CON - TJ APS-001 - Constellation (From by Project) | 1 | Repair | Transactional | Forecast | Waiting PO | May-26 | 2026 | 800 | 3 | [16 empty] | 266.6667 | 266.6667 | 266.6667
Pressure Control | H4 Connector | CON - H4 Connector - Constellation (From by Projects) - SHD - Brava Star - 470005885 | 1 | FPA | FPA | Firm | Concluded | February-26 | 2025 | 1168 | 3 | [7 empty] | 389.3333 | 389.3333 | 139 | 150 | 100 | 170 | 130
Topside | Telescopic Joint - QTR-3500 | CON - TJ GDS-B - Constellation (From by Projects) | 1 | Repair | Transactional | Forecast | Waiting PO | March-26 | 2026 | 800 | 3 | [14 empty] | 266.6667 | 266.6667 | 266.6667
Riser | Riser Joint - QTR-3500 | 52J montagem e ajuste Lone Star - Constellation | 52 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 120 | 1 | [8 empty] | 6240
Riser | Riser Joint - QTR-3500 | 76J Lone Star CSA Scope - Constellation | 76 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 50 | 2 | [7 empty] | 1900 | 1900
Riser | Riser Joint - QTR-3500 | CON - LNS-015 - Investigation - Constellation | 1 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 100 | 2 | [7 empty] | 50 | 50
Topside | Telescopic Joint - QTR-3500 | CON - TJ LNS-001 Urgency - Constellation (From by Project) | 1 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 250 | 1 | [7 empty] | 250
Riser | Riser Joint - QTR-3500 | CON - Pup Joint GDS-095 & APS-115 (From by projects) | 2 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 200 | 2 | [7 empty] | 200 | 200
Others | AHC Cylinders | VEN - 2x Force Equalizer Cylinders | 2 | D&I | Short Cycle | Firm | Concluded | February-26 | 2025 | 150 | 2 | [8 empty] | 50 | 100
Pressure Control | H4 Connector | TOI - H4 Connector - Transocean Corcovado - SHD (From by sales) | 1 | FPA | FPA | Forecast | Waiting PO | August-26 | 2026 | 1168 | 3 | [19 empty] | 389.3333 | 389.3333 | 389.3333
Pressure Control | H4 Connector | TOI - H4 Connector - Transocean KG2 - SHD (From by sales) | 1 | FPA | FPA | Forecast | Waiting PO | May-26 | 2026 | 1168 | 3 | [16 empty] | 389.3333 | 389.3333 | 389.3333
Pressure Control | H4 Connector | TOI - H4 Connector - DWHD - Transocean Corcovado (From by sales) | 1 | FPA | FPA | Forecast | Waiting PO | July-26 | 2026 | 1168 | 3 | [18 empty] | 389.3333 | 389.3333 | 389.3333
Pressure Control | H4 Connector | VLS - H4 Connector - Valaris DS-04 - ExF (From by Sales) | 1 | FPA | FPA | Forecast | Waiting PO | March-26 | 2026 | 1168 | 3 | [14 empty] | 389.3333 | 389.3333 | 389.3333
Topside | Travelling Block | NBL - Travelling Block - Ocean Courage - Noble (From by sales) | 1 | FPA | FPA | Forecast | Waiting PO | March-26 | 2026 | 704 | 3 | [14 empty] | 234.6667 | 234.6667 | 234.6667
Riser | Riser Joint - QTR-3500 | 52J - Riser CSA - Inspection onshore from offshore - Lone Star | 52 | CSA | Short Cycle | Firm | Concluded | February-26 | 2025 | 35 | 1 | [10 empty] | 1820
Riser | Riser Joint - QTR-3500 | 20J Minor Adjustments - Riser CSA - Lone Star | 20 | CSA | Short Cycle | Firm | Concluded | November-25 | 2025 | 30 | 1 | [10 empty] | 600
Riser | Riser Joint - QTR-3500 | 12J Minor Adjustments - Riser CSA - Lone Star SPS | 12 | CSA | Short Cycle | Firm | Concluded | December-25 | 2025 | 30 | 2 | [11 empty] | 180 | 180
Riser | Riser Joint - QTR-3500 | 4J Major Adjustments - Riser CSA - Lone Star SPS | 4 | CSA | Short Cycle | Firm | Concluded | January-26 | 2026 | 330 | 1 | [12 empty] | 1320
Riser | Riser Joint - QTR-3500 | 52J - Riser CSA - Inspection onshore - Lone Star SPS | 52 | CSA | Short Cycle | Firm | Concluded | January-26 | 2026 | 33 | 1 | [12 empty] | 1716
Riser | Riser Joint - QTR-3500 | 81J - Riser CSA - Lone Star SPS - Minor Repair | 81 | CSA | Short Cycle | Firm | WIP | February-26 | 2026 | 66 | 2 | [13 empty] | 2673 | 2673
Riser | Riser Joint - QTR-3500 | 13J - Riser CSA - Lone Star SPS - Minor repair | 13 | CSA | Short Cycle | Firm | WIP | December-26 | 2026 | 66 | 1 | [23 empty] | 858
Riser | Riser Joint - QTR-3500 | 45J - Riser CSA - Gold Star SPS - Minor repair | 45 | CSA | Short Cycle | Firm | WIP | October-26 | 2026 | 66 | 1 | [21 empty] | 2970
Riser | Riser Joint - QTR-3500 | 69J - Riser CSA - Alpha Star - Annual | 69 | CSA | Short Cycle | Firm | WIP | April-26 | 2026 | 33 | 1 | [15 empty] | 2277
Riser | Riser Joint - QTR-3500 | 69J - Riser CSA - Gold Star - Annual | 69 | CSA | Short Cycle | Firm | WIP | September-26 | 2026 | 33 | 1 | [20 empty] | 2277
Riser | Riser Joint - QTR-3500 | 13J - Riser CSA - Lone Star - Annual | 13 | CSA | Short Cycle | Firm | WIP | November-26 | 2026 | 33 | 1 | [17 empty] | 429 |  |  |  |  | 429
Riser | Riser Joint - FT - H | 56J - Riser CSA - Brava Star - Base Line | 56 | CSA | Short Cycle | Firm | WIP | August-26 | 2026 | 150 | 2 | [19 empty] | 4200 | 4200
Riser | Riser Joint - FT - H | 10J - Riser CSA - Laguna Star - Base Line | 10 | CSA | Short Cycle | Firm | WIP | November-26 | 2026 | 150 | 1 | [22 empty] | 1500
Riser | Riser Joint - FT - H | 49J - Riser CSA - Laguna Star - Annual | 49 | CSA | Short Cycle | Firm | WIP | December-26 | 2026 | 38 | 1 | [23 empty] | 1862
Riser | Riser Joint - QTR-3500 | 4J - Riser CSA - Alpha Star - Major Repair | 4 | CSA | Short Cycle | Firm | WIP | April-26 | 2026 | 330 | 1 | [15 empty] | 1320
Riser | Riser Joint - QTR-3500 | 6J - Riser CSA - Gold Star - Major Repair | 6 | CSA | Short Cycle | Firm | WIP | October-26 | 2026 | 330 | 1 | [21 empty] | 1980
Riser | Riser Joint - QTR-3500 | 40J - Riser CSA - Alpha Star SPS - Minor repair | 40 | CSA | Short Cycle | Firm | WIP | June-26 | 2026 | 66 | 1 | [17 empty] | 2640
Pressure Control | Bonnet | FOR - Bonnet ODN I - 47000xxxx | 1 | D&I | Transactional | Firm | Waiting Parts | March-26 | 2026 | 132 | 1 | [14 empty] | 132
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by sales / Addressable) # 1 | 1 | D&I | Transactional | Forecast | Waiting PO | July-26 | 2026 | 132 | 1 | [18 empty] | 132
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by sales / Addressable) # 2 | 1 | D&I | Transactional | Forecast | Waiting PO | July-26 | 2026 | 132 | 1 | [18 empty] | 132
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by sales / Addressable) # 3 | 1 | D&I | Transactional | Forecast | Waiting PO | July-26 | 2026 | 132 | 1 | [18 empty] | 132
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by sales / Addressable) # 4 | 1 | D&I | Transactional | Forecast | Waiting PO | July-26 | 2026 | 132 | 1 | [18 empty] | 132
Pressure Control | Bonnet | CON - Bonnet - Constellation - Lone Star 22-5K (From by sales) | 1 | D&I | Transactional | Forecast | Waiting PO | June-26 | 2026 | 132 | 1 | [17 empty] | 132
Pressure Control | Bonnet | CON - Bonnet - Constellation - Lone Star 15-3K (From by sales) | 1 | D&I | Transactional | Forecast | Waiting PO | June-26 | 2026 | 132 | 1 | [17 empty] | 132
Pressure Control | Bonnet | FOR - Bonnet ODN ¦ - Foresea (From by sales) # 1 | 1 | D&I | Transactional | Forecast | Waiting PO | May-26 | 2026 | 132 | 1 | [16 empty] | 132
Pressure Control | Bonnet | FOR - Bonnet ODN ¦ - Foresea (From by sales) # 2 | 1 | D&I | Transactional | Forecast | Waiting PO | May-26 | 2026 | 132 | 1 | [16 empty] | 132
Pressure Control | Bonnet | FOR - Bonnet ODN ¦¦ - Foresea (From by sales) # 3 | 1 | D&I | Transactional | Forecast | Waiting PO | May-26 | 2026 | 132 | 1 | [16 empty] | 132
Pressure Control | Bonnet | FOR - Bonnet ODN ¦¦ - Foresea (From by sales) # 4 | 1 | D&I | Transactional | Forecast | Waiting PO | May-26 | 2026 | 132 | 1 | [16 empty] | 132
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by sales / Addressable) # 1 | 1 | Repair | Transactional | Forecast | Waiting PO | September-26 | 2026 | 370 | 2 | [20 empty] | 185 | 185
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by sales / Addressable) # 2 | 1 | Repair | Transactional | Forecast | Waiting PO | September-26 | 2026 | 370 | 2 | [20 empty] | 185 | 185
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by sales / Addressable) # 3 | 1 | Repair | Transactional | Forecast | Waiting PO | September-26 | 2026 | 370 | 2 | [20 empty] | 185 | 185
Pressure Control | Bonnet | VEN - Bonnet - Ventura (From by sales / Addressable) # 4 | 1 | Repair | Transactional | Forecast | Waiting PO | September-26 | 2026 | 370 | 2 | [20 empty] | 185 | 185
Pressure Control | Bonnet | CON - Bonnet - Constellation - Lone Star 22-5K (From by sales) | 1 | Repair | Transactional | Forecast | Waiting PO | August-26 | 2026 | 370 | 2 | [19 empty] | 185 | 185
Pressure Control | Bonnet | CON - Bonnet - Constellation - Lone Star 15-3K (From by sales) | 1 | Repair | Transactional | Forecast | Waiting PO | August-26 | 2026 | 370 | 2 | [19 empty] | 185 | 185
Pressure Control | Bonnet | FOR - Bonnet ODN ¦ - Foresea (From by sales) # 1 | 1 | Repair | Transactional | Forecast | Waiting PO | October-26 | 2026 | 370 | 2 | [21 empty] | 185 | 185
Pressure Control | Bonnet | FOR - Bonnet ODN ¦ - Foresea (From by sales) # 2 | 1 | Repair | Transactional | Forecast | Waiting PO | October-26 | 2026 | 370 | 2 | [21 empty] | 185 | 185
Pressure Control | Bonnet | FOR - Bonnet ODN ¦¦ - Foresea (From by sales) # 3 | 1 | Repair | Transactional | Forecast | Waiting PO | October-26 | 2026 | 370 | 2 | [21 empty] | 185 | 185
Pressure Control | Bonnet | FOR - Bonnet ODN ¦¦ - Foresea (From by sales) # 4 | 1 | Repair | Transactional | Forecast | Waiting PO | October-26 | 2026 | 370 | 2 | [21 empty] | 185 | 185
Topside | Drawworks Callipers (MB) | VEN - 14x Brake Callipers - Ventura (From by Sales) | 14 | FPA | FPA | Forecast | Waiting PO | June-26 | 2026 | 20 | 1 | [17 empty] | 280
Topside | Drive Train | VEN - Drive Train DDM 1000 - Ventura - Fleet (From by sales) | 1 | Repair | Transactional | Firm | WIP | March-26 | 2026 | 520 | 2 | [14 empty] | 260 | 260
Pressure Control | Ram Block | VEN - Ram Block - Ventura - Victoria (From by sales) | 2 | D&I | Transactional | Firm | Concluded | February-26 | 2025 | 100 | 1 | [5 empty] | 200
Pressure Control | Ram Block | VEN - Ram Block - Ventura - Victoria (From by sales) - 470005490 | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 250 | 2 | [8 empty] | 125 | 95 | 30
Topside | Telescopic Joint - QTR-3500 | CON - TJ APS-001 - Constellation (From by Project) | 1 | T&A | Transactional | Forecast | Waiting PO | August-26 | 2026 | 640 | 1 | [19 empty] | 640
Others | Offshore | 4 Employee - January | 4 | N/A | Offshore | Firm | Concluded | February-26 | 2026 | 110 | 1 | [12 empty] | 440
Others | Offshore | 4 Employee - February | 4 | N/A | Offshore | Firm | Concluded | February-26 | 2026 | 110 | 1 | [13 empty] | 440
Others | Offshore | 4 Employee - March | 4 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [14 empty] | 440
Others | Offshore | 3 Employee - April | 3 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [15 empty] | 330
Others | Offshore | 3 Employee - May | 3 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [16 empty] | 330
Others | Offshore | 3 Employee - June | 3 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [17 empty] | 330
Others | Offshore | 6 Employee - July | 6 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [18 empty] | 660
Others | Offshore | 6 Employee - August | 6 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [19 empty] | 660
Others | Offshore | 6 Employee - September | 6 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [20 empty] | 660
Others | Offshore | 6 Employee - October | 6 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [21 empty] | 660
Others | Offshore | 6 Employee - November | 6 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [22 empty] | 660
Others | Offshore | 6 Employee -December | 6 | N/A | Offshore | Forecast | Waiting Requested | February-26 | 2026 | 110 | 1 | [23 empty] | 660
Topside | DDM | NBL - DDM Noble - Ocean Courage (From by Sales) | 1 | D&I | Transactional | Forecast | Waiting PO | November-26 | 2026 | 1400 | 2 | [22 empty] | 700 | 700
Pressure Control | Ram Block | VEN - Ram Block - Ventura - Victoria (From by sales) - 470005491 | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2025 | 250 | 2 | [8 empty] | 125 | 95 | 30
Topside | DDM | NBL - DDM Noble - Ocean Courage (From by Sales) | 1 | Repair | Transactional | Forecast | Waiting PO | March-27 | 2027 | 1000 | 3 | [26 empty] | 333.3333 | 333.3333 | 333.3333
Topside | DDM | FOR - DDM Foresea - ODN I (From by Sales) | 1 | D&I | Transactional | Forecast | Waiting PO | April-26 | 2026 | 1400 | 2 | [15 empty] | 700 | 700
Topside | DDM | FOR - DDM Foresea - ODN I (From by Sales) | 1 | Repair | Transactional | Forecast | Waiting PO | July-26 | 2026 | 1000 | 3 | [18 empty] | 333.3333 | 333.3333 | 333.3333
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Inspeção lote 1 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [12 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Inspeção lote 2 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Transocean - Inspeção lote 3 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [14 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Inspeção lote 4 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [15 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Inspeção lote 5 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Transocean - Inspeção lote 6 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Inspeção lote 7 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Inspeção lote 8 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Transocean - Inspeção lote 9 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Inspeção lote 10 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Inspeção lote 11 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Transocean - Inspeção lote 12 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 45 | 1 | [23 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 1 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [12 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 2 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 3 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [14 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 4 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [15 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 5 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 6 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 7 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 8 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 9 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 10 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 11 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Transocean - Repair - Lote 12 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 370 | 1 | [23 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Montagem lote 1 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [12 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Montagem lote 2 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Transocean - Montagem lote 3 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [14 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Montagem lote 4 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [15 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Montagem lote 5 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Transocean - Montagem lote 6 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Montagem lote 7 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Montagem lote 8 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Transocean - Montagem lote 9 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Montagem lote 10 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Transocean - Montagem lote 11 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Transocean - Montagem lote 12 |  | CSA | Short Cycle | Risk Release | Waiting PO | February-26 | 2026 | 77 | 1 | [23 empty] | 0
Riser | Riser Joint - LK - 3.5 | 12J - Riser CSA Ventura - Inspeção lote 4 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [15 empty] | 0
Riser | Riser Joint - LK - 3.5 | 14J - Riser CSA Ventura - Inspeção lote 5 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [16 empty] | 0
Riser | Riser Joint - LK - 3.5 | 14J - Riser CSA Ventura - Inspeção lote 6 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [17 empty] | 0
Riser | Riser Joint - LK - 3.5 | 64J - Riser CSA Ventura - Baseline | 64 | CSA | Short Cycle | Forecast | Waiting PO | July-26 | 2026 | 150 | 2 | [18 empty] | 4800 |  |  | 4800
Riser | Riser Joint - LK - 3.5 | 10J - Riser CSA Ventura - Major Repair | 10 | CSA | Short Cycle | Forecast | Waiting PO | September-26 | 2026 | 310 | 2 | [20 empty] | 1550 | 1550 |  | 1550
Riser | Riser Joint - LK - 3.5 | 54J - Riser CSA Ventura - Minor Repair | 54 | CSA | Short Cycle | Forecast | Waiting PO | August-26 | 2026 | 88 | 5 | [19 empty] | 950.4 | 950.4 | 950.4 | 950.4 | 950.4
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Inspeção lote 5 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Inspeção lote 6 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 6J - Riser CSA Transocean - Inspeção lote 7 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Inspeção lote 8 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Inspeção lote 9 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 6J - Riser CSA Transocean - Inspeção lote 10 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Inspeção lote 11 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Inspeção lote 12 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [23 empty] | 0
Riser | Riser Joint - FT - H | 1J - Riser CSA Transocean - Repair - Lote 4 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [15 empty] | 0
Riser | Riser Joint - FT - H | 2J - Riser CSA Transocean - Repair - Lote 5 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 2J - Riser CSA Transocean - Repair - Lote 6 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 1J - Riser CSA Transocean - Repair - Lote 7 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 2J - Riser CSA Transocean - Repair - Lote 8 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 2J - Riser CSA Transocean - Repair - Lote 9 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 1J - Riser CSA Transocean - Repair - Lote 10 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 2J - Riser CSA Transocean - Repair - Lote 11 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 2J - Riser CSA Transocean - Repair - Lote 12 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [23 empty] | 0
Riser | Riser Joint - FT - H | 6J - Riser CSA Transocean - Montagem lote 4 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [15 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Montagem lote 5 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Montagem lote 6 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 6J - Riser CSA Transocean - Montagem lote 7 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Montagem lote 8 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Montagem lote 9 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 6J - Riser CSA Transocean - Montagem lote 10 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Montagem lote 11 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 7J - Riser CSA Transocean - Montagem lote 12 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [23 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Inspeção lote 1 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Inspeção lote 2 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Seadrill - Inspeção lote 3 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [14 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Inspeção lote 4 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [15 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Inspeção lote 5 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Seadrill - Inspeção lote 6 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Inspeção lote 7 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Inspeção lote 8 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Seadrill - Inspeção lote 9 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Inspeção lote 10 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Inspeção lote 11 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Seadrill - Inspeção lote 12 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 50 | 1 | [23 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 1 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 2 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 3 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [14 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 4 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [15 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 5 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 6 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 7 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 8 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 9 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 10 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 11 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 5J - Riser CSA Seadrill - Repair - Lote 12 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 340 | 1 | [23 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Montagem lote 1 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Montagem lote 2 |  | CSA | Short Cycle | Forecast | Waiting PO | February-26 | 2026 | 20 | 1 | [13 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Seadrill - Montagem lote 3 |  | CSA | Short Cycle | Forecast | Waiting PO | March-26 | 2026 | 20 | 1 | [14 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Montagem lote 4 |  | CSA | Short Cycle | Forecast | Waiting PO | April-26 | 2026 | 20 | 1 | [15 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Montagem lote 5 |  | CSA | Short Cycle | Forecast | Waiting PO | May-26 | 2026 | 20 | 1 | [16 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Seadrill - Montagem lote 6 |  | CSA | Short Cycle | Forecast | Waiting PO | June-26 | 2026 | 20 | 1 | [17 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Montagem lote 7 |  | CSA | Short Cycle | Forecast | Waiting PO | July-26 | 2026 | 20 | 1 | [18 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Montagem lote 8 |  | CSA | Short Cycle | Forecast | Waiting PO | August-26 | 2026 | 20 | 1 | [19 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Seadrill - Montagem lote 9 |  | CSA | Short Cycle | Forecast | Waiting PO | September-26 | 2026 | 20 | 1 | [20 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Montagem lote 10 |  | CSA | Short Cycle | Forecast | Waiting PO | October-26 | 2026 | 20 | 1 | [21 empty] | 0
Riser | Riser Joint - FT - H | 21J - Riser CSA Seadrill - Montagem lote 11 |  | CSA | Short Cycle | Forecast | Waiting PO | November-26 | 2026 | 20 | 1 | [22 empty] | 0
Riser | Riser Joint - FT - H | 22J - Riser CSA Seadrill - Montagem lote 12 |  | CSA | Short Cycle | Forecast | Waiting PO | December-26 | 2026 | 20 | 1 | [23 empty] | 0
Pressure Control | H4 Connector | Forecast Time PCS - 2 |  | N/A | FPA | Forecast | Waiting PO | April-26 | 2026 | 1000 | 3 | [15 empty] | 0 | 0 | 0
Topside | DDM | Forecast Time Topside - 2 |  | N/A | FPA | Forecast | Waiting PO | April-26 | 2026 | 1500 | 3 | [15 empty] | 0 | 0 | 0
Pressure Control | H4 Connector | Forecast Time PCS - 3 |  | N/A | FPA | Forecast | Waiting PO | July-26 | 2026 | 4000 | 3 | [18 empty] | 0 | 0 | 0
Topside | DDM | Forecast Time Topside - 3 |  | N/A | FPA | Forecast | Waiting PO | July-26 | 2026 | 2000 | 3 | [18 empty] | 0 | 0 | 0
Pressure Control | H4 Connector | Forecast Time PCS - 4 |  | N/A | FPA | Forecast | Waiting PO | October-26 | 2026 | 2500 | 3 | [21 empty] | 0 | 0 | 0
Topside | DDM | Forecast Time Topside - 4 |  | N/A | FPA | Forecast | Waiting PO | October-26 | 2026 | 2500 | 3 | [21 empty] | 0 | 0 | 0
Pressure Control | H4 Connector | CON - Upper Body DWHD - Constellation - Laguna Star - 470006394 | 1 | FPA | FPA | Firm | Concluded | November-25 | 2025 | 600 | 1 | [10 empty] | 600
Pressure Control | H4 Connector | CON-Upper Body Repair LNS - Constellation - Lone Star - 470007311 | 1 | Repair | Transactional | Firm | Concluded | February-26 | 2026 | 200 | 1 | [13 empty] | 200
Pressure Control | H4 Connector | CON - Upper body DxE - Constellation - Amaralina Star - 470006117 | 1 | FPA | FPA | Firm | Concluded | January-26 | 2026 | 300 | 2 | [12 empty] | 100 | 200
Pressure Control | H4 Connector | CON - H4 Connector FPA ExF - Constellation - Brava Star - 470006270 | 1 | FPA | FPA | Firm | Concluded | October-25 | 2025 | 700 | 3 | [9 empty] | 380 | 220 | 100
Pressure Control | H4 Connector | CON - H4 Connector FPA DxE - Constellation - Brava Star - 470006272 | 1 | FPA | FPA | Firm | Concluded | October-25 | 2025 | 1168 | 4 | [9 empty] | 389.3333 | 389.3333 | 189 |  | 200
Pressure Control | Shafts and Pumps | VLS - Pulsation Dampner - 470006323 | 1 | D&I | Transactional | Firm | Concluded | December-25 | 2026 | 150 | 1 | [11 empty] | 150
Topside | Telescopic Joint - MR6H | VLS - TJ Valaris - Troca de selos | 1 | N/A | Transactional | Forecast | Waiting PO | March-26 | 2026 | 480 | 1 | [14 empty] | 480
Topside | Telescopic Joint - MR6H | VLS - Bearing System + Inner Barrel TJ Valaris - Aditional Scope - DS08 | 1 | D&I | Transactional | Forecast | Waiting PO | March-26 | 2026 | 600 | 3 | [14 empty] | 200 | 400
Pressure Control | Mandrel | CON- Mandrel - Constellation - 470007305 | 1 | D&I | Transactional | Firm | Concluded | January-26 | 2026 | 60 | 1 | [13 empty] | 60
Pressure Control | Mandrel | CON- Mandrel - Constellation - 470007305 | 1 | Repair | Transactional | Firm | Concluded | January-26 | 2026 | 120 | 1 | [13 empty] | 120
Pressure Control | Mandrel | TOI- Mandrel D&I- Transocean - 470006562 | 1 | Repair | Transactional | Firm | Concluded | January-26 | 2026 | 120 | 2 | [12 empty] | 80 | 40
Pressure Control | Mandrel | TOI- Mandrel D&I- Transocean - 470006562 | 1 | D&I | Transactional | Firm | Concluded | December-25 | 2025 | 80 | 1 | [11 empty] | 80
Topside | Telescopic Joint - MR6H | VLS - Bearing System + Inner Barrel TJ Valaris - Aditional Scope - DS08 | 1 | T&A | Transactional | Forecast | Waiting PO | November-26 | 2026 | 450 | 2 | [22 empty] | 225 | 225
Topside | Telescopic Joint - MR6H | VLS - Bearing System + Inner Barrel TJ Valaris - Aditional Scope - DS08 | 1 | Repair | Transactional | Forecast | Waiting PO | August-26 | 2026 | 800 | 3 | [19 empty] | 266.6667 | 266.6667 | 266.6667
Topside | Telescopic Joint - QTR-3500 | CON - TJ LNS-001 Urgency - Constellation (From by Project) | 1 | D&I | Short Cycle | Firm | Concluded | January-26 | 2026 | 250 | 2 | [12 empty] | 125 | 125
Topside | Telescopic Joint - MR6H | VLS - Bearing System + Inner Barrel TJ Valaris - 470006252 | 1 | D&I | Transactional | Firm | Concluded | November-25 | 2025 | 150 | 1 | [10 empty] | 150
Riser | Riser Joint - FT - H | 1016 Bolts para realização de Xylan | 1016 | CSA | Short Cycle | Firm | Concluded | December-25 | 2025 | 0.2 | 2 | [11 empty] | 101.6 | 101.6
Riser | Riser Joint - LK - 3.5 | VLS - 90 Bolts modification HMF to LK-3.5 - Valaris | 90 | Repair | Short Cycle | Firm | WIP | March-26 | 2026 | 2 | 1 | [14 empty] | 180
Pressure Control | Diverter | CON - Diverter Handling Tool - Constellation | 1 | FPA | FPA | Firm | WIP | February-26 | 2026 | 235 | 2 | [13 empty] | 195 | 40
Pressure Control | H4 Connector | Forecast 1 | 1 | FPA | FPA | Forecast | Waiting PO | January-27 | 2027 | 6000 | 12 | [24 empty] | 500 | 500 | 500 | 500 | 500 | 500
Topside | DDM | Forecast 1 | 1 | FPA | FPA | Forecast | Waiting PO | January-27 | 2027 | 3000 | 12 | [24 empty] | 250 | 250 | 250 | 250 | 250 | 250
Riser | Riser Joint - FT - H | 12J - Riser CSA - Amaralina Star - Base Line | 12 | CSA | Short Cycle | Firm | Waiting Requested | January-27 | 2027 | 135 | 1 | [24 empty] | 1620
Riser | Riser Joint - FT - H | 2J - Riser CSA - Brava Star - Base Line | 2 | CSA | Short Cycle | Firm | Waiting Requested | February-27 | 2027 | 135 | 1 | [25 empty] | 270
Riser | Riser Joint - FT - H | 13J - Riser CSA - Laguna Star - Base Line | 13 | CSA | Short Cycle | Firm | Waiting Requested | February-27 | 2027 | 135 | 1 | [25 empty] | 1755
Riser | Riser Joint - FT - H | 78J - Riser CSA - Amaralina Star - Anual | 78 | CSA | Short Cycle | Firm | Waiting Requested | January-27 | 2027 | 34.2 | 1 | [24 empty] | 2667.6
Riser | Riser Joint - FT - H | 56J - Riser CSA - Brava Star - Annual | 56 | CSA | Short Cycle | Firm | Waiting Requested | March-27 | 2027 | 34.2 | 1 | [26 empty] | 1915.2
Riser | Riser Joint - FT - H | 49J - Riser CSA - Laguna Star - Annual | 49 | CSA | Short Cycle | Firm | Waiting Requested | April-27 | 2027 | 34.2 | 1 | [27 empty] | 1675.8
Riser | Riser Joint - FT - H | 8J - Riser CSA - Amaralina Star - Major Repair | 8 | CSA | Short Cycle | Firm | Waiting Requested | April-27 | 2027 | 279 | 1 | [27 empty] | 2232
Riser | Riser Joint - FT - H | 8J - Riser CSA - Brava Star - Major Repair | 8 | CSA | Short Cycle | Firm | Waiting Requested | May-27 | 2027 | 279 | 1 | [28 empty] | 2232
Riser | Riser Joint - FT - H | 8J - Riser CSA - Laguna Star - Major Repair | 8 | CSA | Short Cycle | Firm | Waiting Requested | June-27 | 2027 | 279 | 1 | [29 empty] | 2232
Riser | Riser Joint - FT - H | 12J - Riser CSA - Amaralina Star - Minor Repair | 12 | CSA | Short Cycle | Firm | Waiting Requested | May-27 | 2027 | 79.2 | 1 | [28 empty] | 950.4
Riser | Riser Joint - FT - H | 12J - Riser CSA - Brava Star - Minor Repair | 12 | CSA | Short Cycle | Firm | Waiting Requested | July-27 | 2027 | 79.2 | 1 | [30 empty] | 950.4
Riser | Riser Joint - FT - H | 12J - Riser CSA - Laguna Star - Minor Repair | 12 | CSA | Short Cycle | Firm | Waiting Requested | July-27 | 2027 | 79.2 | 1 | [30 empty] | 950.4
Riser | Riser Joint - FT - H | 5J - Riser CSA - Alpha Star - Base Line | 5 | CSA | Short Cycle | Firm | Waiting Requested | July-27 | 2027 | 110 | 1 | [30 empty] | 550
Riser | Riser Joint - FT - H | 5J - Riser CSA - Gold Star - Base Line | 5 | CSA | Short Cycle | Firm | Waiting Requested | August-27 | 2027 | 110 | 1 | [31 empty] | 550
Riser | Riser Joint - FT - H | 5J - Riser CSA - Lone Star - Base Line | 5 | CSA | Short Cycle | Firm | Waiting Requested | September-27 | 2027 | 110 | 1 | [32 empty] | 550
Riser | Riser Joint - FT - H | 77J - Riser CSA - Alpha Star - Anual | 77 | CSA | Short Cycle | Firm | Waiting Requested | August-27 | 2027 | 33 | 1 | [31 empty] | 2541
Riser | Riser Joint - FT - H | 77J - Riser CSA - Gold Star - Annual | 77 | CSA | Short Cycle | Firm | Waiting Requested | October-27 | 2027 | 33 | 1 | [33 empty] | 2541
Riser | Riser Joint - FT - H | 77J - Riser CSA - Lone Star - Annual | 77 | CSA | Short Cycle | Firm | Waiting Requested | October-27 | 2027 | 33 | 1 | [33 empty] | 2541
Riser | Riser Joint - FT - H | 10J - Riser CSA - Alpha Star - Major Repair | 10 | CSA | Short Cycle | Firm | Waiting Requested | September-27 | 2027 | 300 | 1 | [32 empty] | 3000
Riser | Riser Joint - FT - H | 10J - Riser CSA - Gold Star - Major Repair | 10 | CSA | Short Cycle | Firm | Waiting Requested | October-27 | 2027 | 300 | 1 | [33 empty] | 3000
Riser | Riser Joint - FT - H | 10J - Riser CSA - Lone Star - Major Repair | 10 | CSA | Short Cycle | Firm | Waiting Requested | November-27 | 2027 | 300 | 1 | [34 empty] | 3000
Riser | Riser Joint - FT - H | 10J - Riser CSA - Alpha Star - Minor Repair | 10 | CSA | Short Cycle | Firm | Waiting Requested | November-27 | 2027 | 66 | 1 | [34 empty] | 660
Riser | Riser Joint - FT - H | 10J - Riser CSA - Gold Star - Minor Repair | 10 | CSA | Short Cycle | Firm | Waiting Requested | November-27 | 2027 | 66 | 1 | [34 empty] | 660
Riser | Riser Joint - FT - H | 10J - Riser CSA - Lone Star - Minor Repair | 10 | CSA | Short Cycle | Firm | Waiting Requested | December-27 | 2027 | 66 | 1 | [35 empty] | 660
Pressure Control | H4 Connector | VLS - Reparo VX / VT Upper SHD - Valaris | 1 | Repair | Transactional | Firm | WIP | March-26 | 2026 | 260 | 1 | [14 empty] | 260

## RCCP SAM
[53 empty] | CATEGORY | 2025 Demand | 2026 Demand | 2027 Demand
Product Line | Equipment | Type | 2025 - Demand (Volumes) | [11 empty] | 2026 - Demand (Volumes) | [11 empty] | 2027 - Demand (Volumes) | [25 empty] | O&R RISER FIRM | 82.9663 | 63.6976 | 38.2468
|  |  | January-25 | February-25 | March-25 | April-25 | May-25 | June-25 | July-25 | August-25 | September-25 | October-25 | November-25 | December-25 | January-26 | February-26 | March-26 | April-26 | May-26 | June-26 | July-26 | August-26 | September-26 | October-26 | November-26 | December-26 | January-27 | February-27 | March-27 | April-27 | May-27 | June-27 | July-27 | August-27 | September-27 | October-27 | November-27 | December-27 | [14 empty] | O&R RISER RISK RELEASE | 0 | 0 | 0
Pressure Control | H4 Connector | Firm | 2129.6 | 1777.6 | 445.1 | 251.5 | 735.5 | 522.8571 | 152 | 822.6667 | 782.6667 | 1341.6667 | 1920.6667 | 764 | 638 | 950 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R RISER FCST | 0 | 19.302 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R RISER TOTAL Hrs. | 82.9663 | 82.9996 | 38.2468
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074.6667 | 778.6667 | 1168 | 389.3333 | 778.6667 | 778.6667 | 778.6667 | 389.3333 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R TOPSIDE FIRM | 23.9276 | 3.854 | 0
| Bonnet | Firm | 211.2 | 821.8667 | 973.8667 | 762.6667 | 352 | 544 | 400 | 400 | 522 | 668 | 600 | 300 | 120 | 30 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R TOPSIDE RISK RELEASE | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R TOPSIDE FCST | 0 | 13.684 | 1.9167
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528 | 660 | 264 | 528 | 370 | 1110 | 1480 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R TOPSIDE TOTAL Hrs. | 23.9276 | 17.538 | 1.9167
| BOP Annular | Firm | 261.6 | 261.6 | 261.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 20 | 270 | 152 | 180 | 278 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R PRESSURE CONTROL FIRM | 29.4604 | 4.708 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R PRESSURE CONTROL RISK RELEASE | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R PRESSURE CONTROL FCST | 0 | 12.124 | 2.5
| Annular Piston | Firm | 424.1667 | 256.6667 | 256.6667 | 256.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R PRESSURE CONTROL TOTAL Hrs. | 29.4604 | 16.832 | 2.5
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | OTHERS FIRM | 8.074 | 1.4 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | O&R OTHERS RISK RELEASE | 0 | 0 | 0
| Male Stab | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | OTHERS FCST | 0 | 6.19 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | OTHERS TOTAL Hrs. | 8.074 | 7.59 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | TOTAL Hrs. | 144.4283 | 124.9596 | 42.6635
| Female Stab | Firm | 0 | 0 | 0 | 124.5 | 0 | 564.5 | 0 | 0 | 360 | 360 | 200 | 160 | 150 | 150 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Current Workshop Capacity per quarter | Headcount | Total Hours
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | HMH Operational Employees | 55 | 19630.6
| Test Stump | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Sub Contractors | 44 | 17505.6933
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Total Employees | 99 | 37136.2933
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Diverter | Firm | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ram Block | Firm | 308.8 | 608.8 | 994.8 | 994.8 | 837.8 | 722 | 800 | 534 | 356 | 470 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ram BOP | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Riser | TJ MR6H (Valaris) | Firm | 400 | 400 | 400 | 0 | 200 | 0 | 0 | 200 | 1000 | 200 | 250 | 100 | 100 | 0 | 350 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 400 | 0 | 0 | 0 | 266.6667 | 266.6667 | 266.6667 | 225 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TJ QTR-3500 | Firm | 1000 | 1450 | 400 | 400 | 880 | 780 | 700 | 910 | 560 | 50 | 0 | 0 | 425 | 505 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266.6667 | 266.6667 | 533.3333 | 266.6667 | 266.6667 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Consolidate Demand per Quarter
| Riser NOV (Batch 5J) | Firm | 0 | 0 | 0 | 0 | 0 | 2867 | 3278 | 600 | 3750 | 4495 | 4070 | 15261.6 | 9476.6 | 6385 | 5200 | 968 | 968 | 0 | 0 | 4200 | 4200 | 0 | 4008 | 4370 | 4287.6 | 2025 | 1915.2 | 3907.8 | 3182.4 | 2232 | 2450.8 | 3091 | 3550 | 8082 | 4320 | 660 |  | 2024 | 2025 |  |  |  | 2026 |  |  |  | 2027
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Status | Q4 - 2024 | Q1 -2025 | Q2 - 2025 | Q3 - 2025 | Q4 - 2025 | Q1 - 2026 | Q2 - 2026 | Q3 - 2026 | Q4 - 2026 | Q1 - 2027 | Q2 - 2027 | Q3 - 2027 | Q4 - 2027
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Riser Firm | 28597.3333 | 21294.6667 | 5727 | 25058 | 30886.6 | 29803.6 | 8602 | 10677 | 14615 | 8227.8 | 7865.2 | 9091.8 | 13062
| Riser QTR-3500 (Batch 5J) | Firm | 6150 | 9430 | 2200 | 1980 | 0 | 880 | 2730 | 4400 | 9690 | 2050 | 4020 | 180 | 3216 | 2673 | 2673 | 3597 | 0 | 3069 | 0 | 0 | 2277 | 4950 | 429 | 858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pressure Control Firm | 6500 | 10301.9333 | 6668.7905 | 5129.3333 | 7360.3333 | 4152 | 556 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Topside Firm | 1807 | 7998.8476 | 5622.3429 | 7135.2381 | 3171.1667 | 3268 | 586 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Offshore & Other Firm | 1700 | 1540 | 2620 | 2604 | 1310 | 1140 | 260 | 0 | 0 | 0 | 0 | 0 | 0
| Riser LK 3.5 (Batch 5J) | Firm | 2490.6667 | 1024 | 0 | 0 | 0 | 0 | 100 | 0 | 510 | 510 | 240 | 60 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Riser Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pressure Control Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 4800 | 950.4 | 2500.4 | 7300.4 | 950.4 | 2500.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Topside Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Topside | DDM | Firm | 863.5714 | 863.5714 | 863.5714 | 863.5714 | 0 | 671.6667 | 671.6667 | 671.6667 | 472 | 250 | 150 | 20 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Offshore & Other Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Riser Forecast | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 8250.8 | 10751.2 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 333.3333 | 333.3333 | 333.3333 | 0 | 700 | 700 | 250 | 250 | 583.3333 | 583.3333 | 583.3333 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | Pressure Control Forecast | 0 | 0 | 0 | 0 | 0 | 1250.6667 | 3920 | 4344 | 2609.3333 | 1500 | 1000 | 0 | 0
| Dolly | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Topside Forecast | 0 | 0 | 0 | 0 | 0 | 1682 | 6560 | 3325.3333 | 2116.6667 | 1083.3333 | 833.3333 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Offshore & Other Forecast | 0 | 0 | 0 | 0 | 0 | 840 | 1390 | 1980 | 1980 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HMH Capacity | 20235.25 | 24156 | 19791.4 | 21494.32 | 21112.4 | 19630.6 | 16261.2 | 17829.6 | 20042 | 20091 | 20091 | 22022 | 22022
| BRC Gripper Head | Firm | 0 | 146.6667 | 293.3333 | 293.3333 | 198 | 309.5238 | 309.5238 | 110 | 200 | 800 | 330 | 522.6667 | 330 | 390 | 330 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Contractors | 32379.25 | 33660 | 28978.6 | 32504.88 | 38466 | 37136.2933 | 21901.12 | 22616.8 | 26774 | 20091 | #N/A | #N/A | #N/A
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Vacation | 6164.75 | 5412 | 8791 | 5314 | 4020.4 | 4642 | 7600 | 8500 | 4642 | 2662 | 2662 | 2662 | 2662
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322.6667 | 622.6667 | 922.6667 | 300 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HMH | 0 | 56 | 56 | 56 | 56 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55
| LGA Guide Head | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249.25 | 249.25 | 180 | 180 | 138 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Contractos | 0 | 18 | 18 | 23 | 38.6667 | 39.6667 | 13 | 10 | 15 | 0 | #N/A | #N/A | #N/A
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Dias Uteis | 0 | 60 | 58 | 64 | 60 | 59 | 58 | 64 | 60 | 60 | 60 | 60 | 60
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Overtime | 38604.3333 | 41135.4476 | 20638.1333 | 39926.5714 | 42728.1 | 42436.2667 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Travelling Block | Firm | 105.6 | 105.6 | 105.6 | 105.6 | 105.6 | 105.7143 | 105.7143 | 150 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Firm + Risk Release + Forecast | 38604.4762 | 41135.4476 | 20638.1333 | 39926.5714 | 42728.1 | 42436.2667 | 21874 | 28577.1333 | 32072.2 | 10811.1333 | 9698.5333 | 9091.8 | 13062
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234.6667 | 234.6667 | 469.3333 | 234.6667 | 234.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Rocker Arm | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Crown Block (Sheave Cluster) | Firm | 0 | 234.6667 | 234.6667 | 234.6667 | 0 | 234.6667 | 234.6667 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234.6667 | 234.6667 | 234.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drawworks Callipers (MB) | Firm | 0 | 0 | 132 | 0 | 0 | 240 | 160 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drawworks Callipers (BKB) | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DATs | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Offshore | Offshore | Firm | 440 | 440 | 440 | 880 | 880 | 440 | 330 | 770 | 440 | 660 | 330 | 220 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 330 | 330 | 330 | 660 | 660 | 660 | 660 | 660 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | Drive Train | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gearbox Draworks | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| BRC Hydraulic Cylinders | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PDPH Hydraulic Cylinders | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AHC Cylinders | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Kelly Valves | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shafts and Pumps | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DDM Torque Wrench | Firm | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wiresheaves | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Riser Running Tool | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gas Handler | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 574 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Goosenecks | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Swivel | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bay Handling | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tensioner | Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Termination Adapter | Firm | 0 | 0 | 0 | 0 | 0 | 200 | 100 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Risk Release | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0